Code Europe

Schedule of Programming left to do

October 2, 1992

These estimates are for programming only; additional time for

design and math model creation (how much things cost, how long things

take, and balancing costs and time to make the game challenging but

possible) must be allowed.

Travel: icons for traveling, i.e., taxi, train, bus, walking; possibly

transitional scenes

build graphic file                      2 hrs

add time and money recording routines   4 hrs

add time and money data to program      4 hrs

hook up icons to correct scenes         2 hrs

NOTE: design and raw data not yet

created!                         several hours (2 days?) required over

and above programming time.

QUESTION: are we going to have transition scenes?  If so, add several more

hours of programming time (1 day?) and some artist's time.

TOTAL: 1.5 days plus 3 days (?)

City names:

get data for all city locations        24 hrs (1 hour per country * 24)

hook up city names                      6 hrs (1/4 hr * 24)

TOTAL: 4 days;    (JPC will do the city locations, 3 days)

Fun facts:

do routines to attach facts to

appropriate cities                   6 hrs

prepare facts for loading from disk    12 hrs (1/2 hr * 24)

do decompress facts from disk routines  6 hrs

do attraction icons at ticket agent

routines                             8 hrs

TOTAL: 4 days     (JPC can prepare the facts, 1.5 days)

Hotels:

build graphic file                      2 hrs

add hotel display routines              8 hrs

add money data to program               6 hrs

NOTE: don't know how hotels function so this estimate is subject to inflation

TOTAL: 2 days

Music:

add music routines                      4 hrs

do code to associate music with country 4 hrs

hook up sound effects                   4 hrs

TOTAL: 1.5 days   (JPC can add the music routines, 0.5 days)

Quiz:

add quiz routine (5 questions          16 hrs

with feedback)

TOTAL: 2 days

Medals at beginning:

add user name input                     4 hrs

add file load and save                 12 hrs

NOTE: need art

TOTAL: 2 days

Puzzle:

add puzzle display routines             16 hrs

TOTAL: 2 days

Pick 3 countries at start of mission:

add prompting and tracking             16 hrs

TOTAL: 2 days

Spot animations for ticket agent

make scripts                            2 times number of anims

add script to program                   2 times number of anims

NOTE: need art

NOTE: need to know how many different

animations there will be

TOTAL: 2 days (assumes 4 animations; tour guide will not animate)

Do tracks from country to country         8 hrs

TOTAL: 1 day

Coordination, meetings, preparing

deliveries                          16-40 hrs

TOTAL: 2-5 days

Install program                            8 hrs

TOTAL: 1 day

Configuration program                      4 hrs

TOTAL: 0.5 days

SUBTOTAL:      27.5 days - 30.5 days

plus design time for math model (2 days?)

plus possible additional time for transition scenes (1 day?)

GRAND TOTAL:   30.5 - 33.5 days

JPC can do 5 days of this, leaving JWM with 25.5 - 28.5 days.

With 21 working days left in October (October 2 - 30), this puts

completion of programming for alpha on Friday, November 6, at the earliest.