Memorandum

DATE:	July 29, 2026

TO:	Walt

FROM:	Cheri

RE:	HTML Publishing on the Internet

CC:	Max

I wanted to outline my strategy on the HTML Publishing on the Internet books and kits. I’ve met with Max several times to discuss the problems and possible solutions for both versions of the HTML Publishing on the Internet books. The problem has recently been amplified with the release of HoTMetaL Pro 2.0 for Windows and the soon to be released version 2.0 for Macintosh. Our possible solutions can be described as taking place in stages.

Our first and foremost task is resolving any of the remaining problems with the current Windows CD. Chris Campana recently let me know that we are about six  weeks away from another printing of the Windows book. Unfortunately, this does not give us enough time to revamp the text of this book. We’ll need to print a small print run (5,000) and include the new and improved CD-ROM. This CD will not include the new version of HoTMetaL Pro. This will ensure that our book does not go out of stock and continues to sell in the channels.

I’ve hired a freelance technical reviewer to test all products on the CD and to make sure that they work in conjunction with each other. I’m paying him out of the $20,000 that Joe allotted for the project. This tester will also let us know which programs need readme files etc. I’m working on ensuring that the version of HoTMetaL Pro has the latest versions of the Netscape rules and video driver patches. I’m also coordinating the effort between Brent and Max to correct other problems that have cropped up on this first CD. Our goal is to have all of these problems addressed in the next printing of the book.

Longer range goals involve revising the text of both books to address version 2.0 changes of HoTMetaL Pro. We’ve held up the Macintosh book for these changes. My plan is to have David and Brent work simultaneously on updating both the Macintosh and Windows versions. Without fully assessing the amount of changes, the tentative schedule is to give both authors three weeks to revamp the text and capture new screen shots. While the authors are working, Max is busy looking for more (and better) software additions to the CD-ROMs. I’ll be acquiring the permissions. We’re also working on a new and improved front end that will make installing and using the CDs much easier and more enjoyable.

The following is a rough schedule that both Max, Pam, and I feel that we can live with (assuming, of course, that our two-stage approach is agreeable to you). The schedule is extremely aggressive.

Stage One: Correction of Current Windows CD

Testing and correcting of current Windows CD problems		8/7 to 8/18

Correction of text problems within current book			8/16

CD material submitted to Fringe for mastering			8/21

Book and CD ready for printing					9/4

Stage Two: Revamped Edition of Windows Version (Book and CD)

Brent Heslop to revise Windows text					8/14 to 9/6

Editorial production 							8/17 to 9/13

CD front engine development						8/2 to 8/15

Products and permissions finalized					8/18

CD submitted to Fringe for mastering				8/21

Book and CD ready for printing					9/19

The following dates are my suggestions for the Macintosh schedule. Pam does not agree with the dates. She wants Jessica to do both books. I would prefer to get both books done simultaneously. Her suggestions appear in parentheses.

Stage Two: Macintosh Version (Book and CD)

David Holzgang to revise Macintosh text				8/14 to 9/6

Editorial production							8/17 to 9/13

CD front engine development

Products and permissions finalized

CD submitted to Fringe for mastering

Book and CD ready for printing					9/19