Team Manager does more than just store information for you. Team Manager can help you consolidate tasks entered by team members, identify issues that need your immediate attention, and keep up with their progress.

chapter 4

Putting Team Manager
to Work for You

Set Up Team Manager to Keep Track of the Details

As the manager, you maintain the team file. Your team members use Team Manager for team members to maintain their own task lists and to see how their tasks fit in with what everyone else is doing. Whenever they add new tasks or change information about existing tasks, they send you update messages, which you accept into your team file. You can also enter information about tasks or people directly into your team file.

In other words, Team Manager keeps the task information in your team file up-to-date by incorporating the task information your team members send you from their individual task lists.

The following pages describe how you use Team Manager to streamline the information-gathering process so that you have more time for coaching team members, planning, organizing, and decision making.

People   Using Team Manager, you can record and organize the information about your team members in one place. You can use Team Manager to review team members’ tasks, record notes about each member, and track their individual progress toward performance goals. This information is private — your team can’t see it using Team Manager for team members.

Tasks   Team Manager gives you and your team the flexibility to enter and define tasks to match the way you work. With regular updates to the team file from team members, you always have a current reading on task status. Team members can use Team Manager for team members to see all task information except notes.

Estimating work   If you and your team members estimate how much work a task will take, Team Manager can help you plan your team’s workload and minimize last-minute crunches. Estimating work also helps you anticipate budget or deadline problems.

Delegating tasks   Although most tasks in the team file will come from team member update messages, you can also enter and delegate tasks. Because Team Manager keeps track of what team members are doing, you can quickly compare workloads to decide who has time to work on a task.

### People

Managing people is probably the most important part of your job as a manager. The more information you have about the people on your team, the more effective you can be as a manager. Team Manager helps you keep track of a wide range of information about your team members.

- For more information about adding people to the People tab, in the Answer Wizard, type:
How do I add someone to my team?

On the People tab, you can see everything you need to know about the people on your team. The information here is not limited to personal data about team members, but includes details about the tasks they are working on, the status of those tasks, and how the tasks fit with team member goals.

Organize information   Information on the People tab is organized by person. If you want to see what Jane Jarvis is working on, you can view all the tasks assigned to her and the status of each one. You can also review her goals to see whether they are compatible with a new task you might delegate.

When you click the arrow on the view banner, a list of available views appears. You use the views on the People tab for the following activities.

Review tasks   If you’re worried that a team member has too much work to complete on time, you can use the Task Assignments view to see information about the tasks currently assigned, such as deadlines, priority, and task status.

Review team member information   Store personal information such as home phone number and address in the Profile Information view. You can also enter cost-tracking information, such as standard and overtime rates.

Record notes   If you want to keep notes about conversations you have with team members, or make a list of items you need to talk to them about, you can use the Notes view. This view lets you enter free-form notes for each team member. You can also format and print these notes.

Track performance goals   If you and a team member agree on a set of performance goals, such as “Increase billable time to 60 percent,” you can monitor progress using the Performance Goals view. For more information about entering and tracking progress toward goals, see “Coach Your Team,” page 84.

View schedules   You don’t have to guess about a team member’s work schedule. Team Manager provides a calendar for listing work days, vacations, and holidays. You can also record a team member’s regularly scheduled working hours.

- For more information about viewing a team member’s schedule, in the Answer Wizard, type:
How do I set working times for someone?

Customize the information displayed in the Profile Information view   Click the Add/Remove Fields button to add a custom row to the Profile Information view. For example, you can record team members’ birthdays or add a row for cellular phone numbers.

### Tasks

Team Manager helps you manage your team to complete tasks on time. Tasks are discrete chunks of work such as “Prepare 1997 budget,” “Write article for newsletter,” and “Evaluate new accounting software.”

The amount of time a task takes, called work, depends on the complexity and nature of the task. Preparing the 1997 budget, for example, might take 70 hours of work, and writing an article for the newsletter might take only four hours of work. Work does not have to be done all at once — a team member could work on preparing the 1997 budget throughout the month, while working on other tasks at the same time.

Tasks are added to your Team Manager team file in several ways:

- For more information about adding tasks to the team file, in the Answer Wizard, type:
How do I add tasks sent by my team?

- Team members enter their own tasks in their individual task lists and send them to you in update messages, which you can accept to incorporate in your team file.

- You enter tasks in the team file yourself.

- A project manager using Microsoft Project sends you a message containing tasks for your team, which you delegate.

When a team member sends you a task, you review the task information and accept it or send it back to the team member with changes.

Use specific task names   When you enter task names, give each task a unique, descriptive name. That way, when you review tasks in Team Manager, or your team members review tasks in their individual task lists, it is always clear which task is which. For example, your team might perform tasks such as “Design prototype,” “Develop process flowchart,” and “Create blueprints” for more than one project. To make it easier to keep track of the tasks, use specific names such as “Design Contoso prototype” and “Develop FreeForm process flowchart.”

You and your team decide how to define the tasks in the team file, but don’t define them too broadly. You should be able to complete a task within a period ranging from a few hours to a few weeks. If tasks last longer than this, your team may find it difficult to assess progress accurately. For example, the task “Market research plan” might be too general.

It’s also not usually a good idea to define tasks too narrowly. For example, in the task “Interview five managers for newsletter article,” the tasks, “Call first manager,” “Write down the comments,” and “Add manager’s comments to article” are too narrow and specific.

Determining when a task definition is just right depends on your team members and your style of management, but Team Manager can help you decide. When you delegate tasks, a team member can return the task update message with corrections or questions. You can then use this feedback to determine whether you’ve clearly defined the task. Similarly, you can ask team members for more information about tasks they send you.

- For more information about defining what kind of task information you exchange with your team, in the
Answer Wizard, type:
How do I add details about tasks?

When you create a new task, you enter information about the task that can help Team Manager (and you) schedule the task and provide you with the information you’ll need later to make decisions about the task.

You can enter the following information about a task (all of these items are optional):

- For more information about task definitions, in the Answer Wizard, type:
Tell me about task properties

- When the task must be completed (the deadline).

- An estimate of the work (how much time it will take to complete).

- How important the task is compared to other tasks (priority).

- Whether other tasks have to finish before the task can start. (For example, “Interview managers” must be completed before “Write article” can start.)

- Constraints, such as required start date.

- Who will do the task.

Work time vs. calendar time

The amount of work required to complete a task is different than the calendar time required.

For example, a task might be to interview five people for a newsletter article. If you estimate one hour for each interview and one hour to write up each interview, the total work time is 10 hours.

The actual interviews, however, might be scheduled over five days (one interview per day). The calendar time to complete this task is five days. This does not mean you assign five days of work to the task. The person working on the task will work on other things when not working on the interviews.

Similarly, work is different than the time between now and the deadline for a task. If the article is due two weeks from today, then the deadline is two weeks from today. It will still take only 10 hours of work to complete the task.

You do not have to be exact or final when you first define a task. With Team Manager, you can change information about ongoing tasks at any time. You can start with a rough estimate of how much work is involved. As work on the task begins, you and your team members can revise the estimate to reflect the actual amount of work the task takes. The more completely you define the properties of the task, the more readily Team Manager can call your attention to potential problems before they happen.

For example, you might initially estimate 10 hours of work for the task “Interview five managers and write up results.” After the first interview, however, your team member reports that it actually took four hours to conduct and write up one interview. At this point you or the team member can revise the work estimate to 20 hours.

In Team Manager, you can enter estimates for some tasks, without specifying work for all tasks. Clearly, if you estimate work for all tasks, you’ll have more reliable information, but you can start by estimating critical tasks.

Advantages to Estimating Work

Whether or not you estimate work, Team Manager will help you and your team manage team activities more smoothly. However, the extra effort you and your team put into estimating work can pay off handsomely.

You spot problems early   When you estimate work, it’s easier to identify potential deadline problems early. Suppose a task is due in two weeks and you estimate that it will require 20 hours of work. Andrea is the best person to work on the job, but she only has 12 hours available. If you assign the full 20 hours of work to Andrea, you’ll know at once that you need to reassign some of Andrea’s work or change the deadline.

You can even out the workload   When you estimate work, you can distribute your team members’ workload more effectively. This way, you can make sure that each team member doesn’t have too much to do.

You know when you can take on more work   Estimating work gives you a better sense of when team members will complete their existing tasks and have time available to take on new ones. This information helps avoid times of no work and times of too much work.

You can keep track of bottlenecks   If you have tasks that must be completed before other tasks can start, estimating work helps you keep track of when these critical tasks will probably be completed.

A method for estimating work is described in “Estimate Work,” page 59.

#### Viewing and Organizing Tasks

Depending on the size of your team and the number of tasks each team member sends you, your team file could grow to include a lot of tasks listed in the order that you accepted them. To help you quickly find just the information you need, Team Manager provides several ways to view and organize your team’s tasks.

As you work with Team Manager, you will discover the views you find most helpful. You can customize the list of views on the view banner to include the ones you use most frequently and hide the ones you don’t use. You can even customize the information that appears in some views to make them more useful.

- For information about customizing views, in the Answer Wizard, type:
How do I tailor my view?

| Helpful ways to look at the tasks in the team file |  |  |
| --- | --- | --- |
| To do this | Use this tab … | … and this view |
| Look at a list of tasks organized by date for all team members | Tasks | Work Calendar |
| Identify tasks or work not yet assigned to a team member | Vital Signs | Tasks with Unassigned Work |
| See tasks with deadlines, sorted by deadline | Vital Signs | Tasks with Deadlines |
| See tasks assigned to a specific team member | People | Task Assignments |
| See the status of tasks | Tasks | Task Status |
| See incomplete tasks with deadlines that have passed, tasks with deadlines that can’t be met, tasks that overload team members, and tasks team members flagged with red alerts | Vital Signs | Tasks that Need Attention |
| Determine how work is distributed across your team | Tasks | Workload Planner |
| Review detailed information about tasks | Tasks | Task Organizer |
| Check estimated start and finish dates for tasks that have work estimates | Tasks | Start-to-Finish Graph |

##### Filtering

When switching views doesn’t give you exactly the information you want, you can temporarily hide the tasks you don’t need to see.

- For more information about filtering, in the Answer Wizard, type:
Tell me about filter information

For example, you might want to see only tasks that share a particular criteria, such as high-priority tasks or tasks in progress. You can filter tasks to hide all tasks that do not have the characteristics you define. Team Manager provides a set of predefined filters, such as Incomplete Tasks, that can be particularly helpful. Or, you can define your own filters.

##### Grouping

Another way to organize your tasks is to group them so that you can focus on the information you need in a particular category.

- For more information about grouping, in the Answer Wizard, type:
Tell me about tasks by category

By People Assigned   You might want to see whether any team member has too many tasks. Use this grouping to see all the tasks arranged by the team member who is working on them.

By Priority   If you want to review your team’s priorities, use this grouping to see all tasks arranged from highest to lowest priority.

By Project   If your team is working on more than one project, you can group the tasks by project name.

By Status   With this grouping, you can see which tasks aren’t started yet and those in various stages of completion.

##### Sorting

Sometimes it is helpful to see a list of tasks in a particular order. In Team Manager you can sort your list, for example, alphabetically by task name or numerically by deadline date or start date.

- For more information about sorting, in the Answer Wizard, type:
How do I sort my tasks?

##### Outlining

Using Team Manager’s outlining tools, you can quickly organize even the most complex tasks into an outline that is easy to understand and follow. For example, the task “Measure product performance” can be broken down into subtasks: “Identify performance indicators,” “Design measurement methods,” and “Determine method reliability.”

- For more information about the outlining tools, in the Answer Wizard, type:
Tell me about organizing my team’s tasks into an outline.

If necessary, you can break down these subtasks into additional subtasks. You can enter all high-level, or summary, tasks at once and then go back and add the subtasks whenever you want. Or drag the tasks your team sends into clusters of related tasks and create summary tasks to organize them. Then use Team Manager views, groups, and filters at any time to see just what you want to see. Or, you can temporarily hide subtasks in order to get a bird’s-eye view of your team’s high-level tasks.

Tip   Team members will only see the subtasks in their individual task lists, so make sure subtasks have unique, descriptive names.

Note   When you filter, group, or sort tasks, you change only what you see in the view. The actual task order in the team file (the order in which tasks were accepted from your team’s update messages or entered or organized by you) doesn’t change.

If you want to permanently change the task order, you can drag task rows or use the outlining tools in a view that is not filtered, grouped, or sorted.

### Estimate Work

If you estimate work, Team Manager becomes a powerful partner to help you manage your team’s schedule and workload. When you estimate work, you can predict costs for your team’s role in a project, forecast the workload for your team members, and make sure that the best people for the task are available.

Estimating work is not simple. Thousands of books have been written on the subject and entire careers built on explaining how to do it. Reading the next few pages won’t make you a professional estimator, but it will give you an approach that you can adapt to your own situation and refine with experience. You’ll probably find that the more you practice estimating, the more accurate your estimates become.

The general approach presented here involves breaking down a project into discrete tasks, each of which is estimated. There are three main steps in this approach.

#### Scaling the Job

When you scale a job, you ascertain its size. The scaling step is crucial to estimating the amount of time the related work will 
take — if you think you have a 30-page document, but you really have a 300-page document, your estimates will be at least 10 times too small.

Scaling can be budget-driven — if you have a $1,000 budget to produce a newsletter, the money determines the scale of the newsletter. When you scale a job, you first look at all the constraints; decide whether they are time-, budget-, or goal-driven; and then figure out what needs to be done to complete the related work within these constraints.

Example

Andrea Loren is asked to produce a company newsletter that is about 10 to 20 pages, without spending too much money. Andrea decides on a 16-page newsletter.

Andrea also estimates that there will be five articles at two pages per article and six pages of news (calendar of company events, awards, and so on).

At the end of the scaling process, Andrea has two different measures of scale: the physical size (16 pages) and the content (five main articles, plus news).

To scale the project, Andrea does not have to specify article topics — this can be worked out later. The goal of scaling is to determine the size of the project.

#### Defining Discrete Tasks

In this step you identify the discrete tasks required to complete the project. A discrete task usually has at least one of the following characteristics:

- Requires specific skill set

- Has particular costs associated with it

- Is a step in a process

- Can be done by a single person

For example, if the project produces a magazine advertisement, then “Illustrating” is a discrete task, because it uses a particular skill set (drawing) with an associated hourly rate (the illustrator’s cost per hour) and can be done by one person (the illustrator). It is also one step in the process of producing the advertisement.

At the end of this step, you should have a list of discrete tasks required to complete the job.

Example

Andrea identifies the following tasks for producing the newsletter:

- Writing (which includes gathering the information)

- Illustrating (drawing any illustrations needed)

- Editing (revising the articles for content and space)

- Copyediting (making sure the articles are grammatically correct)

- Proofreading (correcting any typographical errors)

- Designing (establishing a look for the newsletter)

- Layout (fitting the text to the page)

- Printing (producing the required number of copies)

In this list, several tasks could be done by the same person (editing and copyediting, for example), but they require different skill sets. The editor and the copy editor could be different people.

Again, Andrea is concerned only about the process of creating a newsletter, not its content, because the next time she does the newsletter, the tasks will be the same.

#### Getting Time Estimates for Each Task

Once you identify discrete tasks, you can begin the process of getting time estimates for each task. Note the phrasing: “getting time estimates.” You don’t have to estimate time for each task. You might get more accurate estimates from the team members who do the work than you can determine yourself.

Team Manager facilitates gathering estimates. You can define a task in your team file, assign it to a team member, and then send a message to the assigned person. This team member can estimate the amount of work for the task and send a message with this information back to you. You can then accept it, or ask them to expand on why they think it will take this amount of time. You can continue this give-and-take until you both agree on the estimate.

At this point in the process, don’t confuse getting the time estimate with scheduling. When you ask a team member for an estimate, the individual may reply, “I’m way too busy to deal with that right now, I couldn’t start on it for at least a couple of weeks.”

You are not trying to schedule the task, you are trying to get an estimate for the amount of time it will take, regardless of when it starts.

You also don’t need to worry about the details of how a team member comes up with an estimate. Two illustrators may work differently, but take the same amount of time to finish a task. One spends five hours doing rough sketches and one hour doing the final; the other spends four hours staring at the drawing board and two hours doing the final.

You may need to explore the estimate with a team member to make sure that it’s realistic (can the team member really write a two-page article in half an hour, for example). This part of the process also depends on your knowledge of a team member’s skill.

Example

Andrea can now send the tasks to team members in update messages (without work estimates) for answers to the questions, “How long will it take …”:

- “… to write an article about x?”

- “… to edit 16 pages of text?”

- “… to copyedit 16 pages of text?”

- “… to proofread 16 pages of text?”

- “… to lay out 16 pages of text?”

At this point, Andrea identifies two types of tasks: static tasks (tasks requiring easy-to-estimate amounts of time, such as proofreading) and talent tasks (writing).

For the talent tasks, Andrea may meet with the writers and talk with them about what articles to write (Andrea finally deals with the content of the newsletter), how much research is required, and how much writing time is needed.

Getting answers to these specific questions, although more elaborate and detailed, is still part of the process of getting the estimates from team members.

As team members send her estimates, Andrea can accept them into her team file and quickly determine the total cost of the newsletter, whether it can be completed on time, and who is available to complete it.

#### How Team Manager Schedules Tasks

If you estimate work and define properties (such as deadlines and priorities) for each task, Team Manager can propose a schedule and call your attention to potential conflicts. Your team does not have to do the work in the order scheduled. Typically, there are many schedules your team could follow to get everything done on time. Team Manager simply presents one option.

- For more information about scheduling, in the Answer Wizard, type:
Why did Team Manager schedule my tasks like this?

As you review the schedule that Team Manager develops, you may have questions about why it scheduled a task at a particular time. More importantly, you may want Team Manager to reschedule the task to a different time (you might be aware, for example, that the deadline can slip several days for one client in order to get another client’s project done on time).

To schedule tasks, give Team Manager the following information, in the following sequence:

Last actual or reschedule-from dates

- For more information about setting a specific start date, in the Answer Wizard, type:
How do I schedule a task to begin on a certain date?

- For more information about task relationships, in the Answer Wizard, type:
How do I schedule a task based on another task?

- For more information about setting earliest start date, in the Answer Wizard, type:
How do I schedule a task to begin on or after a certain date?

- No tasks can be scheduled before the last actual or reschedule from date for the people assigned. Team Manager will not schedule anyone before the last actual they reported on a task or the reschedule-from date you entered.

- Must-start-on dates

- If you’ve entered a date on which a task must start, Team Manager attempts to schedule the task to start on this date.

- Task relationships

- If a task can’t start until another task is finished, Team Manager does not schedule the second task until after the finish date for the first task, although other types of relationships are allowed.

- Deadlines and earliest start dates

- If you’ve entered a deadline for a task, Team Manager schedules the task to meet the deadline. If you’ve estimated work, Team Manager also considers the number of hours required for the task. Team Manager does not schedule a task before the earliest start date, if you entered one.

- Priorities

- Team Manager schedules higher priority tasks before lower priority tasks.

- Task ID

- Team Manager assigns a task ID in the order that tasks are added or organized. If all other factors are equal, tasks entered or listed first in the task list are scheduled first.

Other factors that affect scheduling are the number of work hours and the amount of overtime permitted for each team member. Team Manager will not schedule work on nonworking days, but will use overtime hours to meet deadline constraints, if you allow for it.

- For more information about allowing overtime, in the Answer Wizard, type:
Tell me about scheduling with overtime.

Team Manager will not assign overtime to a team member to complete a task unless you specifically allow this.

The most common ways to adjust the schedule are to adjust the priority or to enter a deadline. You can also change the amount of estimated work or assign more people to a task.

### Delegate Tasks

Let’s say that you have a number of tasks to delegate. How do you decide which team members to assign? You can use the information in Team Manager to quickly determine who is available and delegate tasks to them.

- For more information about delegating tasks, in the Answer Wizard, type:
How do I assign a task to someone?

You need two key pieces of information when you want to assign a task: who is qualified to do it and who is available to do it.

Deciding who is qualified to do a task requires your knowledge of your team members’ abilities. Sometimes the best person to assign to a task is not the most qualified person, but rather a person who will be challenged by and learn from the task. Team Manager can help you assess and develop team members’ skills by keeping track of goals that you and team members have set and performance on related tasks. You can review these goals and progress toward meeting them to determine whether the task is a good match for a team member.

For example, if a team member has a goal to “Improve understanding of how customers use our product,” you might select this person for a task that involves researching product improvements.

Once you decide on a person (or confirm that a person is capable), Team Manager can help you quickly evaluate that person’s workload, as described in the next section.

Note   In most cases, team members will add their own tasks to your team file by sending them to you in update messages. This means that the team member has identified a task that needs to be done, feels qualified to do it, and is interested in doing it.

#### Checking the Workload

If you estimate the amount of work per task, Team Manager can help you effectively balance the workload. Team Manager takes into account the number of hours each person works, the priority of the task, and the task deadline as it develops a schedule for a team member. You can use this information to evaluate whether a team member has the time to take on a particular task.

- For more information about redistributing work, in the Answer Wizard, type:
Tell me about reassigning work to adjust workloads

Several views show a person’s assigned tasks, but the most useful view for a quick look at a person’s workload is in the Workload Planner on the Tasks tab. This view presents a graph showing tasks over time. Remember, Team Manager doesn’t schedule — rather it sets aside enough time to get the task completed by the person who is assigned. (Tasks may not be underway just because they are scheduled.)

When you click the Group by People button, the list is organized by team members. You can quickly see which tasks people are working on and when they are available to work on another task.

Tip   When you group by people, you can reassign tasks quickly by dragging tasks from one person’s group to another. Reassigning some of the most qualified person’s tasks to another team member can make the one most qualified immediately available for the new task.

If you don’t estimate work, you can instead enter a deadline for the task. When you do this and the team member sends you status updates, you can use Team Manager to review a team member’s assigned tasks in progress and their deadlines. In Task Status view, you can see how many tasks the team member started, how many are in progress, and how many tasks have work remaining. Also, you can look over any deadlines — if a person has many deadlines close together, the individual may have difficulty meeting them all, so this team member may not be the best person for new tasks. You can use the Sorting command on the View menu to sort the tasks by deadline.

- For more information about grouping, in the Answer Wizard, type:
How do I group tasks by category?

#### Viewing Assigned Tasks

Team Manager shows assigned tasks in several different views. Switch to the view and use the Quick Filter or grouping tools to review only the information you need, without unnecessary or distracting information. Filters hide extraneous information; grouping includes all information, but categorizes it.  XE "Tabs:Tasks"

- For more information about the Quick Filter, in the Answer Wizard, type:
How do I use a Quick Filter?

| Helpful ways to look at assigned tasks |  |  |  |
| --- | --- | --- | --- |
| To do this | Use this tab … | … and this view … | … with this tool |
| Decide which team member has time to take on a new task | Tasks | Workload Planner | Group by People |
| Change priorities | Tasks | Task Organizer | Group by Priority |
| See a person’s tasks for the next two weeks | Tasks | Task Organizer | Quick Filter by People and Dates |
| Review the team’s deadlines from earliest to latest | Vital Signs | Tasks with Deadlines |  |
| See when the tasks for a particular project are scheduled | Tasks | Workload Planner or Work Calendar | Group by Project |
| Review the progress made on each task to find out how soon a team member might be available to take on another task | Tasks | Task Status | Group by People |
| Find out how Team Manager scheduled the tasks for each team member | Tasks | Start-to-Finish Graph | Group by People |
| Find out what an individual team member is working on | People | Task Assignments |  |

Want to suggest a priority change?   When you group by priority, you can drag task rows from one group priority to another to change the priority. When you send updates to the team members assigned to those tasks, they can accept the changes to add to their individual task lists or reject the changes and send messages back to you.

#### Assigning More Than One Person to a Task

One advantage to teamwork is that more than one team member can work on the same task. Using Team Manager, you can assign multiple people to a task or add people to a task already under way. This can be useful, for example, if a deadline is coming up and more help is needed. If two people send you information about a single task that they’re both working on, you can assign the second person to the first task and delete the second task for easier tracking.

	To assign a task to more than one person

- In the Task Organizer on the Tasks tab, click in the People Assigned column in the task row.

- Click the arrow to display a list of team members.

- A selected check box indicates that a team member is already assigned to the task. The estimated amount of work for that person appears to the right (if your team is estimating work).

- Select the check box next to the team member you want to add to the task.

- Any unassigned work will be given to this person.

- If necessary, change the work estimates for each team member to reflect the amount of time each will spend on the task.

- The total amount of work you assign here will appear in the Total Work column after you confirm the change.

- Press ENTER to close the list.

- Press ENTER again to confirm the change.