TELETUTOR

Computer-Based Training Series

LAN: Local Area Networking

Appendix

Copyright 1989, Cooper and Associates Inc., Portsmouth NH 03801

800 - 542 - 2242 or 603 - 433 - 2242

All rights reserved.

TELETUTOR LAN COURSE

APPENDIX

LAN Planning and Management Considerations

The purpose of this Appendix is to provide a compendium of

ideas, observations, and issues to consider before, during

and after the implementation of a LAN.

Planning, installing and administering a large LAN can be a

complex, time consuming process, involving many factors,

judgements, people and actions.  But because every LAN

installation will be different, there is no ONE right way

to approach the task or do the job.

And that's reflected by the way we've organized this

Appendix, as well as by the information it contains.  We

have not tried to provide you with a step-by-step LAN

checklist, because the right checklist for you would

probably be the wrong checklist for someone else.

So our Appendix is designed for browsing.  Within, you may

see lots of items you've already included in your LAN plan,

some items you may have left out inadvertently, and maybe

one or two you never even thought of.  Or better yet,

perhaps something in here will trigger an important new

idea nobody has thought of before.

The Appendix deals with 5 major topics:

-  Project Planning (objectives for your LAN)

-  Current Profile (your current hardware/software/user

environment)

-  LAN Profile (changes needed to implement your LAN)

-  Selection/Implementation (choosing and installing a LAN)

-  Administration/Maintenenace (ongoing operation of a LAN)

Each topic includes a number of sub-topics which are dealt

with in the text.  The table of contents includes a brief

bullet-point summary of the information covered in the text

for that sub-topic.  In this way, the table of contents

provides a quick review of the entire Appendix.

i

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Table of Contents and Summary

PROJECT PLANNING

Goal/Purpose/Objective                ..............  1

- prepare a written statement against which

you can measure plans and progress

- describe why you want a LAN today, and tomorrow

- make objective(s) as concrete as possible (e.g.

share laser printer, provide E-Mail, etc.)

Planning Stage                        ..............  1

- plan for entire project (e.g. LAN selection,

implementation, operation)

- for large nets, consider a planning group

Management Responsibilities           ..............  2

- assign management responsibilities and

sign-offs for each phase of project (one

person, committee, department, etc.)

LAN Budget                            ..............  2

- if pre-set, use to make trade-offs during

planning

- if to be set after planning, offer various

options with pros and cons

- balance cost against performance and needs

Decision Support Data                 ..............  3

collect data for:

- current profile - determine where you are now

(staff, tasks, equipment, etc.)

- proposed LAN profile - determine what's needed

to meet goal

difference between profiles indicates project scope

ii

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

CURRENT PROFILE

Users                                 ..............  4

collect user information

- name

- title

- department name and function

- physical location

- job description

- user expectations and requirements

Hardware Inventory                    ..............  4

collect information about current hardware

- manufacturer

- model name/number

- serial number

- purchase date/warranty

- vendor

- etc.

record data for:

- workstations (PCs and terminals)

size of main memory

operating system

drives (floppy, hard, tape, size/format)

number of expansion slots available

option boards (ports, clock/calendar,

expanded/extended memory, modem,

mouse, fax, etc.)

- special display monitors (graphics, desktop

publishing)

- printers

- plotters

- fax machines

- digitizers

- other peripherals

- modems (or modem cards)

- backup power supply units

- connectors/interfaces, cables

- miscellaneous (power strips, surge

protectors, etc.)

iii

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

CURRENT PROFILE (continued)

Application Software                  ..............  5

collect information on current packages

- product name

- manufacturer

- version number

- license/registration number

- licensing restrictions

- vendor

determine for each package:

- how many copies ?

- location of the documentation?

- location of the master disks?

- networking version available?

applications might include:

- word processing

- spreadsheet

- database

- graphics

- desktop publishing

- CAD

- personal utilities (calendar, clock,

calculator, notepad, etc.)

- modem communications

- integrated packages

- custom application packages

- etc.

iv

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

PROPOSED LAN PROFILE

LAN Users                             ..............  6

consider:

- additions to (or exclusions from) current

profile list

- anticipated staff growth

Hardware Upgrades/Replacements        ..............  6

determine whether to upgrade existing:

- workstations (PCs, terminals)

- memory

- monitors

- peripherals

Network Related Hardware              ..............  6

list new hardware needed for network

- LAN cable

- cable ducts, raceways, trays, etc.

- terminator(s) for a bus

- station interface cards

- station cable

- medium interface

- cable connectors/adapters

- repeaters/splitters/amplifiers/transceivers

- servers (central, disk/file, terminal, print,

communications, etc.)

- headend remodulator for broadband bus

- redundant equipment (servers, headend, etc.)

- backup power supply units

- additional workstations/ diskless workstations

- station hubs and wire centers in a ring

- modems (or modem cards)

- bridges, routers, and/or gateways

- Network Control Center (NCC) station

v

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

PROPOSED LAN PROFILE (continued)

Special Furniture/Supplies            ..............  7

consider the need for:

- special desks/tables for workstations,

printers, plotters, digitizers, fax

machines, servers, etc.

- chairs and anti-static, plastic carpet

protectors

- file cabinets, bookcases, shelves

- ribbon cartridges for printers, ink

cartridges for plotters, toner for

the fax machine, etc.

- paper for printers, plotters, digitizers,

and fax machine

- special forms (e.g. custom accounting invoices

with company logo, name and address)

- blank diskettes and tape cartridges (e.g. for

backups)

- diskette and tape storage cases

- extension cords, plug strips, desk lamps, etc.

- and anything else you can think of!

Application Software                  ..............  7

factors to consider in selecting application

software for the network

- network versions

- legal/licensing issues

- concurrent access issues

additional software

- workgroup utilities (scheduling, calculator)

- e-mail

vi

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

PROPOSED LAN PROFILE (continued)

Remote Access And Security            ..............  8

consider whether to:

- encourage, restrict, avoid remote access?

consider need for:

- communications server

- communications software

- modem pool

- remote access software

consider the security implications of:

- remote access

- local access

- file access

- record access

- hardware access

- power conditioning/backup power supply/ups

- data backup - hardware, media, procedures,

storage

Network Traffic Load                  ..............  11

assess factors influencing traffic load

- number of users

- types of applications

- typical interactions

- frequency of interactions by user/application

consult dp/mis/other experts for advice

LAN Performance                       ..............  11

evaluate proposed LAN performance in terms of:

- speed

- number of users

- throughput

- fault tolerance

consult dp/mis/other experts for advice

vii

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

PROPOSED LAN PROFILE (continued)

Future Expansion                      ..............  12

consider your proposed LAN in terms of:

- ease of expansion (graceful growth)

- future applications

- future interconnection of LANs

LAN Support                           ..............  12

determine who will provide ongoing support

if internal, consider costs for:

- staff

- training

- parts

- tools

- test equipment/software (e.g. time domain

reflectometer, continuity testers, protocol

analyzer)

if vendor/third party, consider:

- service options (annual fee, time & materials)

- reliability and response time

- software update policies

viii

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

SELECTION/IMPLEMENTATION

Select LAN Product                    ..............  14

- decide appropriate mix of topology, media,

access method for your applications

- identify specific products on the market

that meet requirements and budget

- determine effectiveness of documentation for

each prospective product - is it complete,

clear and understandable ?

- consider vendor/manufacturer reputation

- make selection balancing budget, user needs,

and performance requirements against each

product's capabilities and cost

Office Alterations                    ..............  14

plan for any needed alterations

- wiring closet(s)

- new partitions

- additional soundproofing

- electrical power and outlets

- new/additional air conditioning

- choose architect/engineer

- get building permits

- observe fire/safety codes

- allow time for competitive bidding

LAN Floor Plan                       ..............  15

prepare a floor plan indicating the locations of:

- stations (PCs, terminals, servers)

- peripherals (printers, plotters, external

drives, modems, etc.)

- power outlets

- special equipment (e.g. fire extinguishers, air

conditioners, heating equipment, etc.)

- wiring closets

- cable routes

- taps, transceivers

- splitters, amplifiers, repeaters

- gateways, bridges, routers

ix

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

SELECTION/IMPLEMENTATION (continued)

Installation                         ..............  15

- Maintain hardware/software inventory records

as equipment is received/installed (vendor,

serial number, date purchased/installed,

installer, DIP switch settings, etc.)

- prepare a logical map of network (logical

device names and addresses)

- install cable first, tag and label each cable

- keep cable records (station cable type, length,

connectors, vendor, purchase/installation

dates, installer, etc.)

- test cable before adding interface equipment

- add stations after testing cable

- bring up one station at a time

- solve system problems before station problems

- configure network (logins, menus, disk partitions,

permissions, application software, printers, etc.)

Record-Keeping Requirements           ..............  17

collect and keep on file:

- all approved planning documents (current and

proposed profiles, inventories, floor plans,

construction orders, equipment orders, etc.)

- installation documentation (furniture, supplies,

hardware and software, i.e. manufacturer name,

address, phone number; model name/number;

amount of memory for a PC; software version

number, etc.).

- log of installation problems and solutions

- ongoing operation records (problems, traffic)

- user records (passwords, login names, disk

partitions, file access/restrictions, etc.)

x

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

ADMINISTRATION/MAINTENANCE

LAN Training Requirements             ..............  18

consider the cost, time, and staff to provide:

- LAN technology training (e.g. this course)

- end user training

- NOS commands & utilities, applications,

policies & procedures training

- network administrator training

- net management tools & software training

- technician training (maintenance)

Network Administrator                 ..............  18

define role of net administrator in:

- installation

- daily operation

- password assignment/maintenance

- file permissions

- user billing

- access security

- problem reporting

determine whether full/part time job

Need For Network Control Center (NCC) ..............  19

consider an NCC for:

- monitoring usage

- collecting performance statistics

- analyzing traffic patterns

- providing input for ongoing planning

before purchasing an NCC:

- examine its documentation

- determine what training is needed/provided

for its use

Ongoing Administration                ..............  20

develop procedures for keeping records on:

- adds, deletes, moves & changes

- performance monitoring & statistics

- maintenance

- traffic/performance history feeds planning for

future

xi

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Appendix

PROJECT PLANNING

Goal/Purpose/Objective

A written statement of your goal or purpose for installing a

LAN can be a helpful "sanity check" and/or benchmark as the

project moves along.  When you find "... and tomorrow the

world!" comments creeping into your plans, a glance back at

this document may help keep things in perspective.

As with most objectives, the more concrete you can make it,

the better.  "To improve corporate communication" may be an

admirable sentiment, but it's not a very useful objective.

"To improve corporate communication by replacing routine

hard-copy interoffice memos with E-Mail messages" is

heading in the right direction.

At the very beginning of a LAN project, your objective(s)

may have to be more general than concrete, simply because

most of the details will remain undiscovered/undecided.

And you can certainly re-visit and refine your objectives

as you go along.  But anything you are able to specify up

front will help.

Planning Stage

The first order of business in setting up a LAN is to

develop a plan for selecting, implementing and operating

the LAN.

Who develops this plan and what issues need to be considered

depend on your situation.

For example, if you're setting up a LAN to connect 3 PCs in

a medical office to handle billing and word processing, the

issues are relatively few and simple.  It's entirely

possible for one person to take charge of the project, come

up with a plan and see it through to completion.

But if you're considering a large company LAN involving

hundreds of users from many departments using a wide

variety of applications, a much higher degree of planning

and coordination is required.

1

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Planning Stage (continued)                PROJECT PLANNING

Many companies in this situation establish a LAN Planning

Committee to develop a comprehensive master plan for

implementing the LAN.

The Planning Committee usually consists of representatives

from each department or area that will be using the LAN.

Because the technical issues in a large LAN can be very

complex, the Committee should also include someone who can

provide technical guidance, perhaps an in-house technical

expert from the MIS department, or an outside LAN

consultant.

Management Responsibilities

Whether one person or a committee develops the plan,

management responsibilities should be assigned early in the

process.  Because project management is critical to the

successful implementation of a LAN, some one individual

needs to be accountable for directing and coordinating the

overall project.

But since the project may involve different phases

(research, technical analysis, scheduling, installation,

etc.) additional management skills may be required at

different stages.

LAN Budget

Budgeting for a LAN can be simple ("spend what you need

to..."), complex ("show me a complete cost/benefit analysis

for every phase..."), or convoluted ("let's see, if I can

get Marketing to pick up the cost of the database software,

and MIS to share the equipment expense...").

No matter how the process is handled in your organization,

establishing at least a rough budget right at the outset

gives you some idea of what you can afford and may assist

in buying decisions later in the process.

2

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

LAN Budget (continued)                        PROJECT PLANNING

If you have been given a pre-set budget to work within, you

may have to make a number of difficult trade-off decisions

during the planning.  If you need to install cable, get a

rough idea of the labor cost as a first step.  It's often

the single biggest expense, and if that eats up your entire

budget, you won't have to worry about trade-offs; you may

need to re-think your entire plan.

If you'll develop a budget out of the planning process and

"sell" it to higher management, be sure to include options

where appropriate.  If possible, indicate the impact of

various alternatives ("the fast access of a 20 millisecond

hard disk will save 50 person-days of productive time per

year compared to the 40ms disk.")

When you are ready to buy, remember the delicate balance

between keeping costs within budget and meeting users'

needs.  This is critical to the overall success of the LAN.

Decision Support Data

Effective planning for the implementation of a LAN requires

that you collect a lot of data about both your current

situation, and about where you want to be.  Once you have

clear pictures of both, the differences between them will

indicate the scope of the project.

The next two sections of this appendix, called Current

Profile and LAN Profile, offer some suggestions for the

types of data to collect.

3

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

CURRENT PROFILE

User Information

An important step in LAN planning is collecting user

information.  Data such as names, titles, departments,

physical locations, job descriptions and what each user

needs or expects from the LAN will help you identify

related functions and possible interactions between groups.

You'll also learn the number of LAN users you'll have and

where their stations are located.

Hardware Inventory

In addition to collecting user information, you should take

an inventory of the computer hardware currently in use in

areas to be linked by the LAN.

The more complete the inventory, the better prepared you

will be to make decisions about LAN products, additional

equipment, equipment upgrades, and the like.

Be sure to include the manufacturer, the model name/number,

serial number, the purchase date and vendor (for warranty

and servicing purposes), the operating system (and version)

in use, and the amount of main memory in PCs, and so on.

Also note any option boards installed in your PCs (ports,

expanded/extended memory, clock/calendar, fax, modem,

mouse, etc.)  Keep in mind, you'll need an expansion slot

in each machine for the network card.  If some of your PCs

are filled up, you may need to alter their configuration.

Or you may find you can consolidate  existing equipment

from PCs onto a network resource (modems in a communications

server, for example) to save on new purchases.

Don't forget to include statistics about permanent storage

devices, such as disk and tape drives.  You may want to

plan now for dealing with a mixture of 3 1/2" and 5 1/4"

floppies on the network.  Or you may find some large

capacity hard drives, or tape drive units that you could

commandeer for use as central network resources.

The inventory should also include equipment connected to

computers such as terminals, special monitors (for graphic

applications, desktop publishing, etc.) and other

peripherals like printers, plotters, digitizers and fax

machines.  Again, you may wish to redistribute these

resources so they can be shared on the network.

4

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Hardware Inventory (continued)               CURRENT PROFILE

And don't forget the little things - cables, connectors,

adapters, external power supplies, power strips, surge

protectors and so on.  Knowing what you have, where, can

make life easier when it comes to hooking everything

together.

The summary in the Table of Contents offers a list to help

get you started.

Application Software

Prepare an inventory of the application software currently

in use.  What applications are currently running, and why?

What are they used for?  Again, this information will help

you plan for a LAN environment.

As with the hardware, record the product name, manufacturer,

version number, license/registration number, vendor, and

date purchased.

In addition, you may want to note how many copies are in

use, on which machines, where the documentation is located,

and where the master disks (distribution disks) are stored.

Once you have a list of your applications, consider how

they will be used in the LAN.  If your existing software

packages are designed for single users, be sure to check

the licensing agreements.  Many restrict or prohibit LAN

use.

If you want everybody to be able to run these packages on

the LAN,  you'll need to find out if they are available in

multi-user, network versions.  If not, you may have to

search for replacement packages that will run on the LAN.

Another issue to consider at this time is software

standardization.  Suppose you have three different word

processing packages.  When you migrate to the LAN, you

might want to pick one of these packages as the standard

for all LAN users.  This could reduce the training and

support requirements for your LAN.  But remember, it may be

quite a feat to get the users to give up their old

favorites and agree on one standard.

Finally, when conducting your software inventory, keep an

eye out for the personal utilities people use frequently.

You may find a gem or two that you'd like to make available

to everyone.

5

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

LAN PROFILE

LAN Users

In your proposed LAN profile, consider individuals (or even

entire departments) who may not currently use PCs in their

work.  Would equipping them and including them on the net

improve overall productivity?  Or perhaps there are some

current PC users who would gain nothing from connection to

the network.

In addition, give your crystal ball a gaze and consider the

future.  Are there known planned additions to staff in any

of the areas to be served by the LAN?  How likely is a

functional reorganization of existing workgroups?  How

about new functional areas?  What impact would any of

these changes have on your LAN planning?

Hardware Upgrades/Replacements

Review your list of current hardware with an eye to upgrades

or replacements.  Perhaps some PCs will need additional

memory to run LAN application programs (e.g. desktop

publishing).  With many users to share it, perhaps you can

justify a new laser printer, or another plotter.  Or maybe

now is the time to add color graphics capability or a

faster processor to some or all of your workstations.

Network Related Hardware

We've discussed some network-related hardware in this

Course.  You'll need to consider servers, network interface

cards, LAN and station cabling, cable connectors/adapters,

repeaters, splitters, amplifiers, transceivers and so on.

Some of this new equipment is dependent on your LAN

topology, media and access method (e.g. transceivers on a

CSMA/CD baseband coax bus).  Some may be strictly a matter

of choice.  Do you wish to tie a fax machine into the

network, or add a laser printer for everyone to share?

You may also need additional PCs.  If your LAN has a

central server for storing files, you might consider buying

diskless workstations.  They cut costs and improve

security, since it's impossible to make copies of files at

these workstations.

6

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Network Related Hardware (continued)             LAN PROFILE

If you're installing a large network, you may also want to

consider a separate Network Control Center station.  See

the Administration/Maintenance section for more on NCCs.

The possibilities are endless.  To help get you started,

the summary in the Table of Contents provides a list of

possible current and network related hardware.

Special Furniture/Supplies

The time to think about odds and ends like printer paper,

replacement ribbons and special printer stands is during

the planning stage for your LAN.  Keep in mind that

consumables for a shared LAN resource will be used up more

quickly than at a single user workstation.  And don't

forget any special forms you may need (invoices with the

company logo, for example, or shipping labels). They might

need to be redesigned for use on LAN printers.

Try to make a list of any special furniture or supplies

you'll need so you can order them early.  The summary in the

Table of Contents includes a number of items to get you

started.

Application Software Requirements

Use your Current Profile software inventory to select any

packages that should be available on your LAN and verify

that network versions are available.

Also keep in mind the legal ramifications of living with a

LAN.  Most of your single user software has probably been

licensed for only one user or machine.  If such software is

allowed to proliferate around the LAN, you may be breaking

the law.  So check the licensing agreements carefully.

When choosing network software, consider how it manages

concurrent access by multiple users.  If two users each

take a copy of the same file, make changes and then upload

it back to the server, the second copy will overwrite the

first and wipe out those changes.  To prevent this, some

type of file or record locking scheme is needed.

7

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Application Software Requirements (continued)      LAN PROFILE

File and record locking schemes are discussed in Lesson 5.

They can be implemented through the Network Operating

System (NOS), the application software (e.g. database

packages), or through an interaction of both.  Again, the

main issue is not how locking is implemented but that it is

available and provides the level of control to meet your

needs.

Also, when selecting network software, consider workgroup

utilities.  These packages may allow all LAN users to

improve communication, scheduling, and productivity.

Electronic mail packages can be used for internal

communication.  Scheduling and calendar maintenance

programs allow users to maintain meeting room schedules or

personal appointment books.  Desktop calculator programs

let users perform quick computations on their workstations.

Remote Access and Security Requirements

Offering remote access to your LAN is an issue that demands

careful thought.  Outgoing off-net access may be important

if your LAN users need the services of public databases,

for example.  Incoming access may be required if you need

to support telecommuters or field service workers, for

example.

If you choose to provide remote access, you'll need a

communications server on the LAN, one or more modems (modem

pool) and a network-compatible communications software

package.  If you're equipping at-home workers, they'll each

need a modem and communications software as well.  You

might also explore some of the remote-access software

packages.  These allow a remote PC to dial in and run an

application on the called PC.

But do consider the security aspects of remote access.  If

there's a modem on your LAN, you are at least somewhat

vulnerable to the predations of unknown computer-snoops,

disgruntled ex-employees, corporate espionage, computer

viruses, and so on.  While there are many steps you can

take to prevent unauthorized access (passwords, encryption,

dial-back modems, anti-viral software, etc.) you must

balance the benefits of remote access with the risks.

8

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Security Requirements                          LAN PROFILE

Security is an important dimension of LAN planning.  If

you're going to offer remote access, for example, you must

decide how to control that access.  Will a simple login

password scheme be sufficient?  Or will you decide on

dial-back modems?  (A dial-back modem asks the caller to

enter a password, then hangs up and calls back to the phone

number associated with that password.)

Even local access, however, requires some security

considerations.  Most LANs require each user to enter a

personal password to log onto the network.  But additional

levels of security may also be implemented.

You may want to consider limiting physical access to some or

all of the network resources, and certainly to servers and

wiring closets.  If the cleaning crew accidentally unplugs

the server while  someone is trying to update a file, you

could end up with scrambled data.  If any stranger in the

office can power up a workstation, who knows what havoc

they might wreak.

In addition, network access to some resources (the

communications server, for example) may be password

protected.  Individual files or directories of files (the

new marketing plans, for example) may be password

protected.  The contents of some files (the company's

payroll records, for example) may be password protected and

encrypted.  Even if someone can guess the password, they

must know the encryption key in order to "decode" the

contents of the file.

These are but a few of the ways access security may be

implemented.  The exact methods and level of security

supported can vary with each LAN product.  So when you're

shopping for your LAN, check out each LAN's security

features and make sure they're adequate to address your

company's needs.  You may want to explore separate

application software packages to implement security

measures as well.

If managing access to data is a key issue, preventing the

total loss of data is even more critical.  Suppose a

payroll clerk accidentally deletes all the payroll related

files.  If there's no backup copy of the files, not only is

the data lost but the employees won't get paid either.

9

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Security Requirements (continued)            LAN PROFILE

Data backup is vital to any system, but especially to a LAN.

You need a backup utility (often included as part of the

Network Operating System) that allows you to make backup

copies of your operational files to floppy disk, tape or

even another hard disk.

Tapes are commonly used for LAN backups because they can

hold the large amount of data on a LAN.  To record the data

on tapes, you'll need a tape drive (often called a tape

streamer), and the software to run it.

It's also important to develop backup procedures.  For

instance, who will do backups, and how often? Daily,

weekly, monthly?  Will you back up all files or only those

changed since the last backup? How will the tapes be

labeled?  By date, by type of backup, etc.?  How about

backup storage (fireproof box, off-site location)?  How

long will backup tapes be retained before they are reused?

(At least two generations is a good place to start.)

In addition to backing up data, give some thought to power

backup systems as well.

Suppose there's a power failure while you're creating a new

document and you haven't yet saved a copy to disk.  Zap,

your document is gone!  Or what if a bolt of lightning

strikes your LAN and fries all the equipment.  The LAN

would be disabled and might cost a pretty penny to fix.

A backup power and surge protection unit not only warns you

of a power failure, but provides a source of power long

enough for you to save your document.  And the surge

protection feature prevents power surges from reaching your

equipment.  No more French fried chips!

Backup power supplies, often referred to as Uninterruptable

Power Supplies (UPS), come in many sizes to provide power

for single or multiple machines for different periods of

time.  Some switch on instantly after a power failure,

others provide continuous power.  Selecting the right

one(s) for your LAN is best left to a technical expert.

10

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

LAN PROFILE

Potential Network Traffic Load

Potential traffic load on the network is dependent on many

factors, all of which interact with each other.  The sheer

number of users is one factor, but the types of

applications they run, the  kinds of interactions required

(short "bursty" messages, or long file transfers, for

example), and the frequency of such interactions must also

be considered.

You'll need this kind of information to determine whether

your proposed LAN will meet the real world requirements of

your users.

Because the issues influencing traffic load are so numerous

and complex, many companies rely on the technical expertise

of their MIS staff or an outside consultant to determine

the potential.

LAN Performance Requirements

Once you know the traffic load, you can determine its impact

on the performance of your proposed LAN.

You may find you'll need a LAN offering a higher

transmission speed or different access method than

originally anticipated to satisfy the traffic requirements.

Or, you might decide to set up two (or three) LANs instead

of one.  Or, you might discover that a LAN won't work at

all and you need to find another alternative.

LAN performance, like traffic load analysis, is a complex

issue involving many factors.  It is often discussed in

terms of throughput, meaning the amount of user data passed

over the network in a given period of time.  But throughput

is an elusive quantity.  For example, a LAN supporting 100

users may be transmitting at 10 Mb/s, but because of

collisions and the overhead bits required to control

transmission, the actual throughput might be reduced to

only 2 or 3 Mb/s.

So, once again, in matching LAN performance to your needs, it

may be wise to rely on the technical expertise of the MIS

staff or a consultant.

11

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

LAN Performance (continued)                LAN PROFILE

And one final point about LAN performance - fault tolerance.

How well can your LAN tolerate faults without failing?  On

a ring, can the LAN detect and bypass a failed station?  Or

on a headend bus, do you have a backup headend device that

takes over if the master fails?  How about a disk failure

on a server, or a cable break, or ...  Designing your

proposed LAN for fault tolerance can help insure a

successful implementation.

Future Expansion Requirements

When considering a LAN, it's important to look beyond your

immediate requirements.  Suppose your LAN can accommodate

up to 100 users.  If the LAN gets popular (and it will),

what will you do if the user base expands to 150?

Or suppose you install a baseband LAN now.  Then, down the

road, you need to install a TV security system.  Since the

digital baseband LAN can't handle analog TV signals, you'll

have to install a separate cable system for the TV.  But if

your crystal ball had shown the future, you might have

installed a broadband (analog) LAN  instead.  Then one

cable system could support both the LAN and TV security

system.

Or perhaps there are already several other LANs around the

company, or maybe you are proposing the initial

implementation of a number of independent LANs.  If, at

some later date you might want to interconnect any or all

of them, give that task some thought now.  Find out what

bridge, router, or gateway products might allow you to tie

them all together.

Planning ahead now can save you major headaches and expense

later.

LAN Support Requirements

In planning your LAN consider how you will handle problems

and support after installation.

Some companies hire, train and equip their own maintenance

staff, and stock spare parts.  For a small company with few

problems, that can get expensive.

12

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

LAN Support Requirements (continued)      LAN PROFILE

Many companies prefer to rely on the LAN vendor (or a third-

party service company) for support.  But this raises its

own issues.  What kinds of service options are offered,

what do they include, how much do they cost, how reliable

is the service provider, and so on.

Two common service options are purchasing a yearly support

contract, or paying for each repair on an hourly basis

(generally referred to as "time and materials").  The

annual contract may include more "goodies" (telephone

support, for example, or free software updates) than the

time and materials approach, but they'll be reflected in

its cost.  Time and materials may seem less expensive, but

you'll have to pay for false alarms (someone tripped over

the server's power cord).

Before choosing a service provider, it's always a good idea

to check with a few of the vendor's other customers to

determine reliability.  Is the vendor responsive to service

calls, and are problems resolved quickly and successfully

(no return visits required)?

Also, check the vendor's policies on updates and new

releases of LAN software.  Updates generally fix known

software problems, while new releases not only correct

problems but also provide new and enhanced features.

If an update corrects a major software problem, it may be

free.  But you might have to pay for non-critical updates

and new releases.  Often, with a support contract, both are

free.  So check with the vendor before you buy.

13

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

SELECTION/IMPLEMENTATION

Select Product

When the planning is done and the data collected, it's time

to select a LAN product.  (Check the Course Glossary under

LAN Products, Vendors and References for a place to start.)

As we've mentioned earlier, you probably will want to rely

on your MIS Department or an external LAN consultant to

help you sort through all the data you've collected and

make the final choice.

After you identify the LAN products that support your choice

of topology, media, and access method, determine the cost

of each.  It's wise to review each vendor's product

documentation to see if it's complete, clear, and

understandable.  If it's not, then the end users, network

administrator, and technicians will have a poor reference

guide to help them figure out how to use advanced features

and commands or how to troubleshoot problems.

Be sure to consider the reputations of both manufacturers

and vendors of products under consideration.  Today's best

deal might become tomorrow's white elephant if neither

company is around to support you.

In the end, the final selection of a LAN product will be

made by balancing your budget, user needs, and performance

requirements against the capabilities and cost of each

vendor's product.

Office Alterations

When planning for installation, don't forget about possible

alterations to your office space.  For example, you may

want to build a wiring closet, put up soundproof

partitions, install more electrical outlets or put in a

large industrial air conditioner.

Depending on the complexity of the alterations, you may need

the services of an engineer or architect to plan them and

insure that all building and fire codes are met.

Competitive bidding with contractors may also be necessary,

so be sure to include this time in your planning.

14

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

SELECTION/IMPLEMENTATION

LAN Floor Plan

A LAN floor plan can be a useful tool for planning

installation.  It is a vital part of the records after

installation.

The floor plan should show the location of all stations

(PCs, terminals, servers, etc.), peripherals (printers,

plotters, etc.), network devices (transceivers, repeaters,

etc.), wiring closets and any special equipment (e.g. fire

extinguishers, air conditioners, etc.)

The floor plan should also include all cable routes, whether

the cable is strung along the wall, under a raised floor,

above a hung ceiling, through ducts between floors, or

through special under-floor or cellular floor systems.

Two words of warning about laying cable.  First, avoid

running cable near sources which might introduce unwanted

noise on your LAN (electric motors, air conditioners, etc.)

Second, allow adequate space, especially through ducts that

must traverse sharp corners.  (Stringing coax through a

long narrow duct with several right angle turns is

difficult at best.)

And if you're using a bus topology, it's wise to show the

location of each transceiver on the cable route, making

sure they're a minimum of 2.5 meters apart and in easily

accessible locations for installation and repair.

Installation

Installation of each LAN is unique, but here are a few basic

tips to remember.

Maintain hardware/software inventory records as equipment is

received.

Establish a logical map of the LAN during and after

installation (e.g. establish logical device name of each

physical device, determine which resources each LAN device

can access both by physical and logical name, etc.).

15

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Installation (continued)          SELECTION/IMPLEMENTATION

Install all the cable first, tagging and labeling cables to

each station for easy identification (particularly where

multiple cables are connected in a wiring closet).  This

can be very helpful when a service person needs to find a

specific cable to fix a problem.

Before adding any of the interface hardware, test the cable.

It will be easier to identify a cable problem if all you're

testing is the cable itself.

When bringing a new LAN up the first time, the generally

accepted wisdom says "bring up one station at a time, and

solve system problems before individual station problems."

If you've tested the cable, but can't get the first station

up and running, the problem lies either in the station, or

in the system.  So try to bring up a second station.  If

that one does come up, the problem lies with the first

station rather than the system.  In that case, continue to

bring up the stations (one at a time).  Then go back and

fix station 1.

If the second station does not come up, the symptoms point

to a system level problem.  Try to find it, then go back to

bringing up stations.

Keep records on the installation of each station.  What kind

of network interface was used (vendor, serial number, date

purchased and installed, installer, etc.)  How were the

DIP switches (if any) set?  What is the station's logical

device name and network address?  What kind of cable

connects the station to the network?  (Type, length,

connectors, vendor, purchase and installation dates,

installer, etc.).  This information can be invaluable for

troubleshooting later.

And of course, record any problems encountered during

installation and how they were resolved.  After all, if you

have a problem and record the solution, you can use that

information to diagnose and fix a similar problem later.

Finally, configure the network.  Create user login names and

passwords, set up disk partitions, establish file and

resource access rights and restrictions and so on.

16

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

SELECTION/IMPLEMENTATION

Record-Keeping Requirements

You've already gathered a lot of information in completing

the Current Profile and the Proposed LAN Profile.  And that

record-keeping should continue throughout the project.

Depending on the size of the LAN, the record-keeping

function may require a full-time commitment, or even the

services of several employees.

During installation, keep records on all the furniture,

supplies, hardware, and software received (i.e.

manufacturer name, address, and phone number; model

name/number; amount of memory for a PC; software version

number; etc.).  Also keep track of how the network was put

together and maintain a log of any problems encountered in

the process (and their solutions!)

Once the LAN is operational, you'll need to keep ongoing

records of system performance, problems, solutions,

reconfiguration information, user and device moves, and the

like.  This data can be invaluable in improving system

performance and helping to plan for future upgrades or

expansion.

One final thought on records.  If you have no records and

the person who set up your LAN decides to leave the

company, you may never figure out how your network

operates.

17

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

ADMINISTRATION/MAINTENANCE

Training Requirements

Training is critical to LAN success.  You should

consider four categories of training:

- LAN technology training

- End user training

- Network Administrator training

- Technician training

This Course is an example of LAN technology training.  It

provides the basic knowledge needed to begin planning and

implementing a LAN.

The other three types of training are LAN product-specific.

End user training covers the Network Operating System (NOS)

commands and utilities (how to log in, access a file or

program, use a network resource, etc.).  It must also

include training on LAN policies and procedures as well as

the application programs available.

Network Administrator training goes a step further and

deals with how to use network management tools and

software.  Technician training must provide maintenance and

repair information for technicians in companies with their

own maintenance crews.

Be sure to factor the cost of training into your overall

plan.  If you're going to do it yourself, allocate time and

personnel to develop and implement your program.  If you go

outside, a good place to start is your LAN vendor.

Network Administrator

Every LAN needs a Network Administrator to take charge of

the installation and daily operation of the network.

Typically, the Network Administrator is responsible for

administrative functions such as adding or deleting users,

assigning user passwords, network addresses, and file

access privileges, installing and configuring applications,

and the like.  If a chargeback system is in effect, the

Administrator may handle billing users for LAN services.

The Network Administrator also takes care of maintenance

tasks, such as detecting problems and reporting them to

initiate corrective action.

18

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

Network Administrator (continued)     ADMINISTRATION/MAINTENANCE

In addition, the Network Administrator monitors the network

to keep track of device usage, performance statistics,

traffic patterns, and so on.  This information is typically

recorded in a database (or two or three) for later

analysis, customer billing, and ongoing planning.

The Network Administrator may also be responsible for

documentation and training.  This includes any policy or

procedure manuals to govern the use of the network and any

training needed by personnel involved with the LAN.

And finally, the Network Administrator must maintain

network security to prevent unauthorized access to the LAN.

If you're setting up a LAN in a small company, these tasks

are often performed on a part-time basis by one of the LAN

users.  But in a large corporation, a full-time Network

Administrator is generally needed.

Need for Network Control Center (NCC)

In larger nets, some type of centralized Network Control

Center (NCC) is often the best (if not the only) way to

efficiently manage the network.  An NCC is a special

workstation on the network that provides a user-friendly

interface for performing administration, maintenance,

monitoring, and other network management functions.

A database in the NCC provides a traffic history for the

network.  It can record such items as how many messages of

what types and what size are being transmitted by each

station; how many stations are active; how many errors

occur, or collisions, or lost or duplicated tokens.  It

will record station problems, and, depending on the

diagnostics available, test individual stations and/or the

network as a whole.

Analysis of this performance and traffic data can be useful

in planning future changes to the LAN.

NCCs are intended to make life easier, but setting them up

and learning how to use them can be difficult.  So before

you invest in one, be sure to at least check its

documentation.  If that's incomprehensible, the NCC may not

do you much good.  And even if the documentation is clear,

verify that the vendor is willing and able to provide the

training you'll need to use the NCC effectively.

19

Copyright 1989, Cooper and Associates Inc., Portsmouth NH

ADMINISTRATION/MAINTENENCE

Ongoing Administration

Once your LAN is up and running, administration and

maintenance become ongoing.  Procedures for handling all

routine tasks and record-keeping should be implemented.

Typically, the Network Administrator handles such day-to-

day administrative tasks as adding new users, deleting

users who leave the company, managing individual or

departmental moves, changing file access privileges,

generating bills, and updating all these administrative

records.

Maintenance procedures should include monitoring for system

problems and failures, running diagnostics, and

identifying/resolving hardware and software problems.

Maintenance also involves monitoring overall system

performance and traffic patterns and keeping relevant

statistics.

All of this information (including the administrative

history) feeds back into ongoing planning for future LAN

development.

For example, suppose a group of LAN users complain about

poor performance and want to upgrade to a higher speed LAN.

With proper historical records and statistics, a traffic

analysis might reveal that a small group of CAD workstation

users are bogging down the system.  Rather than upgrading,

the best solution here might be to put the CAD users on a

separate network.

Accurate, up-to-date records provide useful information for

improving system performance and deciding on future

changes.  When it's time to divide an existing large LAN

into two smaller ones; to provide additional connections

between LANs; to upgrade to a higher speed LAN; to install

additional server capacity or whatever, you won't have to

resort to the old executive decision-making dartboard.

With historical data available, the information will be

there to help you plan effectively.

20

Copyright 1989, Cooper and Associates Inc., Portsmouth NH